## Raptors - Low
Ctech Estimate - ROM Raptors Tunnel (Landscape, Low)
Prepared Sep 18 2026 ¦ CAD $ excl. HST ¦ one projection wall ¦ rate CAD $220/h ¦ hours and non-projector costs are [U] estimates
Project Materials
Qty | Description | Unit Price | Extended | Ordered | Notes | Links | Qty - shared / projector 1 | Qty - projector 2
2 | Epson PowerLite 770F UST laser projector - landscape | 2854 | 5708 | 0 | [V] CAD unit price read Sep 18 2026 from Epson Canada. [U] selection / quantity; stock and rear-fabric test not confirmed. | https://epson.ca/For-Work/Projectors/Classroom/PowerLite-770F-1080p-3LCD-Ultra-Short-Throw-Lamp-Free-Laser-Display/p/V11HA79020 | 1 | 1
1 | Playback PC + visitor tracking kit [U] | 3100 | 3100 | 0 | PC CAD $1,500-2,500 plus two depth cameras, USB / power, mounts and shipping CAD $1,600-2,400 [U] budget allowance. Candidate: Orbbec Femto Bolt. Coverage / compatibility requires prototype. | https://www.orbbec.com/products/tof-camera/femto-bolt/ | 1 | 0
1 | Finished white rear-projection fabric panel | 700 | 700 | 0 | [U] allowance; retains 15 x 8 ft wall panel. Image band is 15 x 4.5 ft. Sample-test UST performance. | https://www.rosebrand.com/softscreen-122-in-ifr-white [US] | 1 | 0
1 | Two landscape mounts and perimeter screen tensioning | 800 | 800 | 0 | [U] allowance: mounts 500-1,000 plus tensioning 300-800. Main tunnel structure excluded. | N/A | 1 | 0
1 | Two video feeds, adapters, power and network cables | 450 | 450 | 0 | [U] allowance: video 200-400 plus power / control 250-600. Do not use a mirroring splitter. | N/A | 1 | 0
1 | Rear bay + shipping + software / asset [U] | 1500 | 1500 | 0 | Rear-bay blackout / shipping CAD $700-1,800 plus commercial playback software / licensed animated raptor CAD $800-1,400 [U] budget. Actual licence and asset quotes not obtained. | https://derivative.ca/UserGuide/Movie_File_In_TOP | 1 | 0
1 | Materials contingency | 3064.5 | 3064.5 | 0 | [U] 25% contingency for a design still being tested. Edit percentage in A60. | N/A | 1 | 0
|  | Project Materials Subtotal | 15322.5
|  | Round to | 15400
Project Hours - Shared design, development and testing
Qty | Description | Unit Price | Extended |  | Notes / estimate basis [U]
12 | Procurement and design | 220 | 2640 |  | Design 6-12 h + procurement 6-12 h: projection layout, two overhead depth cameras, position-to-frame mapping and sourcing.
12 | Research and Development | 220 | 2640 |  | Prototype 12-24 h: fabric / UST test plus camera coverage, camera handoff, visitor position and bidirectional video scrubbing.
28 | Programming | 220 | 6160 |  | Programming 28-56 h: projection playback 12-24 h plus tracking 16-32 h. Map one visitor position to video frame, smooth forward / reverse, hold when stopped, reset on exit / loss.
12 | Integration | 220 | 2640 |  | Integration 12-24 h: projector / camera mounts, USB and power, camera handoff calibration, projection alignment and media preparation. No custom PCB.
10 | Testing | 220 | 2200 |  | Testing 10-20 h: seams, brightness / colour, person walking / stopping / reversing, entry / exit, camera handoff and reverse playback performance.
4 | QA | 220 | 880 |  | QA 4-8 h: tracking loss / re-entry, restart recovery and soak setup / review. Unattended soak time is not billed.
42 | Heavy-use hardening | 220 | 9240 |  | Public deployment uplift x1.4: add 40% of base project hours, rounded up. Covers recovery, durable mounting / cabling and operator reliability.
6 | Documentation | 220 | 1320 |  | Documentation 6-12 h: projection and camera layout, calibration, media / configuration backups and operator handover.
8 | Content Development | 220 | 1760 |  | Content development 8-16 h: source an existing licensed animated raptor, make one side-view walking-across-wall clip, simple background, one review / revision and export for forward / reverse scrubbing. No bespoke modelling.
24 | Buffer | 220 | 5280 |  | 25% buffer on design + prototype + programming + integration + content after x1.4 uplift. Design-only hours are in A58.
158 |  | Shared labour subtotal | 34760 |  | Total labour hours including installation |  | 170
Project Hours - On-site installation and commissioning
Qty | Description | Unit Price | Extended |  | Notes / estimate basis [U]
0 | Procurement and design | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Research and Development | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Programming | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Integration | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Testing | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | QA | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Heavy-use hardening | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Documentation | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
12 | Install and commissioning | 220 | 2640 |  | Install 12-24 person-hours: transport, projection setup, camera mounting / calibration, visitor walk tests and venue handover. One installation; no ongoing attendance.
0 | Buffer | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
12 |  | Installation subtotal | 2640 |  | Calendar weeks [U]: 30 h/week, x1.3 approvals |  | 8
|  | Total tech estimate | 52800
Cost breakdown (materials unrounded)
| Shared labour + shared hardware / projector 1 + contingency |  | 47228.5
| Installation labour + projector 2 hardware |  | 5494
| Image width per projector | ft | 8
| Image height per projector | ft | 4.5
| Combined projected width | ft | 15
25% | Iteration buffer [U] - editable percentage | 1.3 | Calendar approval multiplier [U]
40% | Public deployment uplift [U] - editable 40% (x1.4 total) | 30 | Focused hours/week [U]
Assumptions
Scope: one 15 x 4.5 ft wall, two landscape USTs, one raptor video and one tracked visitor. Two overhead depth cameras provisionally allowed.
| Rate supplied by Garrett; edit C57. HST excluded. | 220
6 | LOW scenario. Base design-only hours in A58 feed the buffer. All labour hours are [U] planning estimates.
1 | Overlap between the two 8 ft wide images: 1 ft [U]. Edit overlap in A59; combined width is calculated in D52.
25% | Materials contingency: 25% [U]. Edit percentage in A60. Shared equipment and contingency are allocated to projector 1.
Nominal optical throw: 8 ft x 0.25 = 2 ft [U calculation]. Complete mounting / cooling / access envelope remains unverified.
Reserve 3-3.5 ft rear-bay depth provisionally [U]; verify model-specific mounting height and physical clearance before fabrication.
Use tensioned diffuse rear-projection fabric. Keep framing and exterior branding out of the beam paths and translucent screen back.
Assume familiar depth / playback tools, wired indoor installation. New technology adds x1.5-2 to affected work (not applied). Asset and camera compatibility unverified.
Excludes bespoke raptor modelling / rigging, additional scenes, multi-person following, audio / sound design, main tunnel fabrication and ongoing attendance.
Follow behaviour: map visitor position to clip frame. Stops hold a frame. Backward steps reverse the clip (raptor backpedals). Exit / lost tracking resets.
Prototype camera coverage, handoff and video scrubbing before committing. Calendar assumes 30 focused h/week, x1.3 approvals. Lead times and real hardware unverified.

## Raptors - High
Ctech Estimate - ROM Raptors Tunnel (Landscape, High)
Prepared Sep 18 2026 ¦ CAD $ excl. HST ¦ one projection wall ¦ rate CAD $220/h ¦ hours and non-projector costs are [U] estimates
Project Materials
Qty | Description | Unit Price | Extended | Ordered | Notes | Links | Qty - shared / projector 1 | Qty - projector 2
2 | Epson PowerLite 770F UST laser projector - landscape | 2854 | 5708 | 0 | [V] CAD unit price read Sep 18 2026 from Epson Canada. [U] selection / quantity; stock and rear-fabric test not confirmed. | https://epson.ca/For-Work/Projectors/Classroom/PowerLite-770F-1080p-3LCD-Ultra-Short-Throw-Lamp-Free-Laser-Display/p/V11HA79020 | 1 | 1
1 | Playback PC + visitor tracking kit [U] | 4900 | 4900 | 0 | PC CAD $1,500-2,500 plus two depth cameras, USB / power, mounts and shipping CAD $1,600-2,400 [U] budget allowance. Candidate: Orbbec Femto Bolt. Coverage / compatibility requires prototype. | https://www.orbbec.com/products/tof-camera/femto-bolt/ | 1 | 0
1 | Finished white rear-projection fabric panel | 1600 | 1600 | 0 | [U] allowance; retains 15 x 8 ft wall panel. Image band is 15 x 4.5 ft. Sample-test UST performance. | https://www.rosebrand.com/softscreen-122-in-ifr-white [US] | 1 | 0
1 | Two landscape mounts and perimeter screen tensioning | 1800 | 1800 | 0 | [U] allowance: mounts 500-1,000 plus tensioning 300-800. Main tunnel structure excluded. | N/A | 1 | 0
1 | Two video feeds, adapters, power and network cables | 1000 | 1000 | 0 | [U] allowance: video 200-400 plus power / control 250-600. Do not use a mirroring splitter. | N/A | 1 | 0
1 | Rear bay + shipping + software / asset [U] | 3200 | 3200 | 0 | Rear-bay blackout / shipping CAD $700-1,800 plus commercial playback software / licensed animated raptor CAD $800-1,400 [U] budget. Actual licence and asset quotes not obtained. | https://derivative.ca/UserGuide/Movie_File_In_TOP | 1 | 0
1 | Materials contingency | 4552 | 4552 | 0 | [U] 25% contingency for a design still being tested. Edit percentage in A60. | N/A | 1 | 0
|  | Project Materials Subtotal | 22760
|  | Round to | 22800
Project Hours - Shared design, development and testing
Qty | Description | Unit Price | Extended |  | Notes / estimate basis [U]
24 | Procurement and design | 220 | 5280 |  | Design 6-12 h + procurement 6-12 h: projection layout, two overhead depth cameras, position-to-frame mapping and sourcing.
24 | Research and Development | 220 | 5280 |  | Prototype 12-24 h: fabric / UST test plus camera coverage, camera handoff, visitor position and bidirectional video scrubbing.
56 | Programming | 220 | 12320 |  | Programming 28-56 h: projection playback 12-24 h plus tracking 16-32 h. Map one visitor position to video frame, smooth forward / reverse, hold when stopped, reset on exit / loss.
24 | Integration | 220 | 5280 |  | Integration 12-24 h: projector / camera mounts, USB and power, camera handoff calibration, projection alignment and media preparation. No custom PCB.
20 | Testing | 220 | 4400 |  | Testing 10-20 h: seams, brightness / colour, person walking / stopping / reversing, entry / exit, camera handoff and reverse playback performance.
8 | QA | 220 | 1760 |  | QA 4-8 h: tracking loss / re-entry, restart recovery and soak setup / review. Unattended soak time is not billed.
84 | Heavy-use hardening | 220 | 18480 |  | Public deployment uplift x1.4: add 40% of base project hours, rounded up. Covers recovery, durable mounting / cabling and operator reliability.
12 | Documentation | 220 | 2640 |  | Documentation 6-12 h: projection and camera layout, calibration, media / configuration backups and operator handover.
16 | Content Development | 220 | 3520 |  | Content development 8-16 h: source an existing licensed animated raptor, make one side-view walking-across-wall clip, simple background, one review / revision and export for forward / reverse scrubbing. No bespoke modelling.
47 | Buffer | 220 | 10340 |  | 25% buffer on design + prototype + programming + integration + content after x1.4 uplift. Design-only hours are in A58.
315 |  | Shared labour subtotal | 69300 |  | Total labour hours including installation |  | 339
Project Hours - On-site installation and commissioning
Qty | Description | Unit Price | Extended |  | Notes / estimate basis [U]
0 | Procurement and design | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Research and Development | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Programming | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Integration | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Testing | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | QA | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Heavy-use hardening | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Documentation | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
24 | Install and commissioning | 220 | 5280 |  | Install 12-24 person-hours: transport, projection setup, camera mounting / calibration, visitor walk tests and venue handover. One installation; no ongoing attendance.
0 | Buffer | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
24 |  | Installation subtotal | 5280 |  | Calendar weeks [U]: 30 h/week, x1.3 approvals |  | 15
|  | Total tech estimate | 97380
Cost breakdown (materials unrounded)
| Shared labour + shared hardware / projector 1 + contingency |  | 89206
| Installation labour + projector 2 hardware |  | 8134
| Image width per projector | ft | 8
| Image height per projector | ft | 4.5
| Combined projected width | ft | 15
25% | Iteration buffer [U] - editable percentage | 1.3 | Calendar approval multiplier [U]
40% | Public deployment uplift [U] - editable 40% (x1.4 total) | 30 | Focused hours/week [U]
Assumptions
Scope: one 15 x 4.5 ft wall, two landscape USTs, one raptor video and one tracked visitor. Two overhead depth cameras provisionally allowed.
| Rate supplied by Garrett; edit C57. HST excluded. | 220
12 | HIGH scenario. Base design-only hours in A58 feed the buffer. All labour hours are [U] planning estimates.
1 | Overlap between the two 8 ft wide images: 1 ft [U]. Edit overlap in A59; combined width is calculated in D52.
25% | Materials contingency: 25% [U]. Edit percentage in A60. Shared equipment and contingency are allocated to projector 1.
Nominal optical throw: 8 ft x 0.25 = 2 ft [U calculation]. Complete mounting / cooling / access envelope remains unverified.
Reserve 3-3.5 ft rear-bay depth provisionally [U]; verify model-specific mounting height and physical clearance before fabrication.
Use tensioned diffuse rear-projection fabric. Keep framing and exterior branding out of the beam paths and translucent screen back.
Assume familiar depth / playback tools, wired indoor installation. New technology adds x1.5-2 to affected work (not applied). Asset and camera compatibility unverified.
Excludes bespoke raptor modelling / rigging, additional scenes, multi-person following, audio / sound design, main tunnel fabrication and ongoing attendance.
Follow behaviour: map visitor position to clip frame. Stops hold a frame. Backward steps reverse the clip (raptor backpedals). Exit / lost tracking resets.
Prototype camera coverage, handoff and video scrubbing before committing. Calendar assumes 30 focused h/week, x1.3 approvals. Lead times and real hardware unverified.