## Raptors - Low
Ctech Estimate - ROM Raptors Tunnel (Landscape, Low)
Prepared Sep 18 2026 ¦ CAD $ excl. HST ¦ one projection wall ¦ rate CAD $220/h ¦ hours and non-projector costs are [U] estimates
Project Materials
Qty | Description | Unit Price | Extended | Ordered | Notes | Links | Qty - shared / projector 1 | Qty - projector 2
2 | Epson PowerLite 770F UST laser projector - landscape | 2854 | 5708 | 0 | [V] CAD unit price read Sep 18 2026 from Epson Canada. [U] selection / quantity; stock and rear-fabric test not confirmed. | https://epson.ca/For-Work/Projectors/Classroom/PowerLite-770F-1080p-3LCD-Ultra-Short-Throw-Lamp-Free-Laser-Display/p/V11HA79020 | 1 | 1
1 | Playback PC - two independent 1080p video outputs | 1500 | 1500 | 0 | [U] allowance; verify GPU outputs and actual playback performance. Shared by both projectors. | N/A | 1 | 0
1 | Finished white rear-projection fabric panel | 700 | 700 | 0 | [U] allowance; retains 15 x 8 ft wall panel. Image band is 15 x 4.5 ft. Sample-test UST performance. | https://www.rosebrand.com/softscreen-122-in-ifr-white [US] | 1 | 0
1 | Two landscape mounts and perimeter screen tensioning | 800 | 800 | 0 | [U] allowance: mounts 500-1,000 plus tensioning 300-800. Main tunnel structure excluded. | N/A | 1 | 0
1 | Two video feeds, adapters, power and network cables | 450 | 450 | 0 | [U] allowance: video 200-400 plus power / control 250-600. Do not use a mirroring splitter. | N/A | 1 | 0
1 | Rear service-bay blackout, shipping and consumables | 700 | 700 | 0 | [U] allowance: blackout 500-1,200 plus shipping / brokerage / consumables 200-600. Keep cooling and service access. | N/A | 1 | 0
1 | Materials contingency | 2464.5 | 2464.5 | 0 | [U] 25% contingency for a design still being tested. Edit percentage in A60. | N/A | 1 | 0
|  | Project Materials Subtotal | 12322.5
|  | Round to | 12400
Project Hours - Shared design, development and testing
Qty | Description | Unit Price | Extended |  | Notes / estimate basis [U]
8 | Procurement and design | 220 | 1760 |  | Design 4-8 h + procurement 4-8 h: layout, optical placement review, screen / mounting plan, sourcing and receiving.
8 | Research and Development | 220 | 1760 |  | Full-size rear-fabric proof of concept 8-16 h. Test focus, hotspots and viewing angles using one candidate projector.
12 | Programming | 220 | 2640 |  | Playback / projection-control software 12-24 h: two independent outputs, mapping, blending and supplied animation playback. No visitor tracking.
8 | Integration | 220 | 1760 |  | Integration 8-16 h: mounting / enclosure preparation 4-8 h plus bench configuration and alignment 4-8 h. No custom PCB.
6 | Testing | 220 | 1320 |  | Testing 6-12 h: two-projector seam, brightness / colour matching, screen tension adjustments and content playback.
2 | QA | 220 | 440 |  | QA 2-4 h: complete-wall acceptance checklist, power restart and soak setup / review. Unattended soak time is not billed as labour.
23 | Heavy-use hardening | 220 | 5060 |  | Public deployment uplift x1.4: add 40% of base project hours, rounded up. Covers recovery, durable mounting / cabling and operator reliability.
4 | Documentation | 220 | 880 |  | Documentation 4-8 h: wiring / layout records, configuration backup and operator handover.
0 | Install and commissioning | 220 | 0 |  | On-site install is priced in the installation block below. Zero here avoids counting it twice.
12 | Buffer | 220 | 2640 |  | 25% iteration buffer on design + prototyping + programming + integration after x1.4 uplift. Rounded up; design-only hours are in A58.
83 |  | Shared labour subtotal | 18260 |  | Total labour hours including installation |  | 91
Project Hours - On-site installation and commissioning
Qty | Description | Unit Price | Extended |  | Notes / estimate basis [U]
0 | Procurement and design | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Research and Development | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Programming | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Integration | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Testing | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | QA | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Heavy-use hardening | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Documentation | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
8 | Install and commissioning | 220 | 1760 |  | Install / commissioning 8-16 person-hours: transport / loading, setup, alignment, cable dressing and venue handover. One installation; no ongoing attendance.
0 | Buffer | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
8 |  | Installation subtotal | 1760 |  | Calendar weeks [U]: 30 h/week, x1.3 approvals |  | 4
|  | Total tech estimate | 32420
Cost breakdown (materials unrounded)
| Shared labour + shared hardware / projector 1 + contingency |  | 27728.5
| Installation labour + projector 2 hardware |  | 4614
| Image width per projector | ft | 8
| Image height per projector | ft | 4.5
| Combined projected width | ft | 15
25% | Iteration buffer [U] - editable percentage | 1.3 | Calendar approval multiplier [U]
40% | Public deployment uplift [U] - editable 40% (x1.4 total) | 30 | Focused hours/week [U]
Assumptions
Scope: two landscape USTs, one 15 x 4.5 ft projected band, flat rear-fabric wall. Approved visual assets supplied by others.
| Rate supplied by Garrett; edit C57. HST excluded. | 220
4 | LOW scenario. Base design-only hours in A58 feed the buffer. All labour hours are [U] planning estimates.
1 | Overlap between the two 8 ft wide images: 1 ft [U]. Edit overlap in A59; combined width is calculated in D52.
25% | Materials contingency: 25% [U]. Edit percentage in A60. Shared equipment and contingency are allocated to projector 1.
Nominal optical throw: 8 ft x 0.25 = 2 ft [U calculation]. Complete mounting / cooling / access envelope remains unverified.
Reserve 3-3.5 ft rear-bay depth provisionally [U]; verify model-specific mounting height and physical clearance before fabrication.
Use tensioned diffuse rear-projection fabric. Keep framing and exterior branding out of the beam paths and translucent screen back.
Assume familiar playback software, wired connections and indoor installation. New-to-you technology adds x1.5-2 to affected work; not applied here.
Excludes original animation / sound production, tracking, audio, software licences, main tunnel fabrication, extra sites and ongoing attendance.
Materials carried unchanged from preceding estimate. Scope-specific labour added here; full raptor-following activation is not priced.
Next action: full-size fabric / UST prototype. Calendar estimate assumes 30 focused h/week and x1.3 client approval allowance; lead times remain unverified.

## Raptors - High
Ctech Estimate - ROM Raptors Tunnel (Landscape, High)
Prepared Sep 18 2026 ¦ CAD $ excl. HST ¦ one projection wall ¦ rate CAD $220/h ¦ hours and non-projector costs are [U] estimates
Project Materials
Qty | Description | Unit Price | Extended | Ordered | Notes | Links | Qty - shared / projector 1 | Qty - projector 2
2 | Epson PowerLite 770F UST laser projector - landscape | 2854 | 5708 | 0 | [V] CAD unit price read Sep 18 2026 from Epson Canada. [U] selection / quantity; stock and rear-fabric test not confirmed. | https://epson.ca/For-Work/Projectors/Classroom/PowerLite-770F-1080p-3LCD-Ultra-Short-Throw-Lamp-Free-Laser-Display/p/V11HA79020 | 1 | 1
1 | Playback PC - two independent 1080p video outputs | 2500 | 2500 | 0 | [U] allowance; verify GPU outputs and actual playback performance. Shared by both projectors. | N/A | 1 | 0
1 | Finished white rear-projection fabric panel | 1600 | 1600 | 0 | [U] allowance; retains 15 x 8 ft wall panel. Image band is 15 x 4.5 ft. Sample-test UST performance. | https://www.rosebrand.com/softscreen-122-in-ifr-white [US] | 1 | 0
1 | Two landscape mounts and perimeter screen tensioning | 1800 | 1800 | 0 | [U] allowance: mounts 500-1,000 plus tensioning 300-800. Main tunnel structure excluded. | N/A | 1 | 0
1 | Two video feeds, adapters, power and network cables | 1000 | 1000 | 0 | [U] allowance: video 200-400 plus power / control 250-600. Do not use a mirroring splitter. | N/A | 1 | 0
1 | Rear service-bay blackout, shipping and consumables | 1800 | 1800 | 0 | [U] allowance: blackout 500-1,200 plus shipping / brokerage / consumables 200-600. Keep cooling and service access. | N/A | 1 | 0
1 | Materials contingency | 3602 | 3602 | 0 | [U] 25% contingency for a design still being tested. Edit percentage in A60. | N/A | 1 | 0
|  | Project Materials Subtotal | 18010
|  | Round to | 18100
Project Hours - Shared design, development and testing
Qty | Description | Unit Price | Extended |  | Notes / estimate basis [U]
16 | Procurement and design | 220 | 3520 |  | Design 4-8 h + procurement 4-8 h: layout, optical placement review, screen / mounting plan, sourcing and receiving.
16 | Research and Development | 220 | 3520 |  | Full-size rear-fabric proof of concept 8-16 h. Test focus, hotspots and viewing angles using one candidate projector.
24 | Programming | 220 | 5280 |  | Playback / projection-control software 12-24 h: two independent outputs, mapping, blending and supplied animation playback. No visitor tracking.
16 | Integration | 220 | 3520 |  | Integration 8-16 h: mounting / enclosure preparation 4-8 h plus bench configuration and alignment 4-8 h. No custom PCB.
12 | Testing | 220 | 2640 |  | Testing 6-12 h: two-projector seam, brightness / colour matching, screen tension adjustments and content playback.
4 | QA | 220 | 880 |  | QA 2-4 h: complete-wall acceptance checklist, power restart and soak setup / review. Unattended soak time is not billed as labour.
45 | Heavy-use hardening | 220 | 9900 |  | Public deployment uplift x1.4: add 40% of base project hours, rounded up. Covers recovery, durable mounting / cabling and operator reliability.
8 | Documentation | 220 | 1760 |  | Documentation 4-8 h: wiring / layout records, configuration backup and operator handover.
0 | Install and commissioning | 220 | 0 |  | On-site install is priced in the installation block below. Zero here avoids counting it twice.
23 | Buffer | 220 | 5060 |  | 25% iteration buffer on design + prototyping + programming + integration after x1.4 uplift. Rounded up; design-only hours are in A58.
164 |  | Shared labour subtotal | 36080 |  | Total labour hours including installation |  | 180
Project Hours - On-site installation and commissioning
Qty | Description | Unit Price | Extended |  | Notes / estimate basis [U]
0 | Procurement and design | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Research and Development | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Programming | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Integration | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Testing | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | QA | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Heavy-use hardening | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
0 | Documentation | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
16 | Install and commissioning | 220 | 3520 |  | Install / commissioning 8-16 person-hours: transport / loading, setup, alignment, cable dressing and venue handover. One installation; no ongoing attendance.
0 | Buffer | 220 | 0 |  | Zero: this phase is included in the shared work block. No duplicate charge.
16 |  | Installation subtotal | 3520 |  | Calendar weeks [U]: 30 h/week, x1.3 approvals |  | 8
|  | Total tech estimate | 57700
Cost breakdown (materials unrounded)
| Shared labour + shared hardware / projector 1 + contingency |  | 51236
| Installation labour + projector 2 hardware |  | 6374
| Image width per projector | ft | 8
| Image height per projector | ft | 4.5
| Combined projected width | ft | 15
25% | Iteration buffer [U] - editable percentage | 1.3 | Calendar approval multiplier [U]
40% | Public deployment uplift [U] - editable 40% (x1.4 total) | 30 | Focused hours/week [U]
Assumptions
Scope: two landscape USTs, one 15 x 4.5 ft projected band, flat rear-fabric wall. Approved visual assets supplied by others.
| Rate supplied by Garrett; edit C57. HST excluded. | 220
8 | HIGH scenario. Base design-only hours in A58 feed the buffer. All labour hours are [U] planning estimates.
1 | Overlap between the two 8 ft wide images: 1 ft [U]. Edit overlap in A59; combined width is calculated in D52.
25% | Materials contingency: 25% [U]. Edit percentage in A60. Shared equipment and contingency are allocated to projector 1.
Nominal optical throw: 8 ft x 0.25 = 2 ft [U calculation]. Complete mounting / cooling / access envelope remains unverified.
Reserve 3-3.5 ft rear-bay depth provisionally [U]; verify model-specific mounting height and physical clearance before fabrication.
Use tensioned diffuse rear-projection fabric. Keep framing and exterior branding out of the beam paths and translucent screen back.
Assume familiar playback software, wired connections and indoor installation. New-to-you technology adds x1.5-2 to affected work; not applied here.
Excludes original animation / sound production, tracking, audio, software licences, main tunnel fabrication, extra sites and ongoing attendance.
Materials carried unchanged from preceding estimate. Scope-specific labour added here; full raptor-following activation is not priced.
Next action: full-size fabric / UST prototype. Calendar estimate assumes 30 focused h/week and x1.3 client approval allowance; lead times remain unverified.